## Project Plan Summary
/Non Project/PSP for Engineers/Program 1
PSP0 Project Plan Summary
Project Owner | Gerardo Granados
Start Date | 2021-02-19 17:14
Completion Date | 2021-02-19 |  |  |  | Completed: ☑
Keywords
Language | Python 3
Time in Phase (min.) | Plan | Actual | To Date | To Date %
Planning |  | 0.0069444 | 0.0069444 | 15.9%
Design |  | 0.0048611 | 0.0048611 | 11.1%
Code |  | 0.015972 | 0.015972 | 36.5%
Compile |  | 0.015972 | 0.015972 | 36.5%
Test |  | 0 | 0 | 0%
Postmortem |  | 0 | 0 | 0%
Total | 0.041667 | 0.04375 | 0.04375
Defects Injected |  | Actual | To Date | To Date %
Before Development |  | 0 | 0 | 0%
Planning |  | 0 | 0 | 0%
Design |  | 1 | 1 | 20%
Code |  | 4 | 4 | 80%
Compile |  | 0 | 0 | 0%
Test |  | 0 | 0 | 0%
Total Development |  | 5 | 5
Defects Removed |  | Actual | To Date | To Date %
Planning |  | 0 | 0 | 0%
Design |  | 0 | 0 | 0%
Code |  | 1 | 1 | 20%
Compile |  | 4 | 4 | 80%
Test |  | 0 | 0 | 0%
Total Development |  | 5 | 5
After Development |  | 0 | 0
PSP materials copyright © 2018 Carnegie Mellon University, licensed under CC BY 4.0.

## Time Recording Log
Proyecto/Tarea | Fase | Tiempo Inicio | Delta | InterrupciÃ³n | Comentario
/Non Project/PSP for Engineers/Program 1 | Planning | 2021-02-19 17:14 | 10 | 0
/Non Project/PSP for Engineers/Program 1 | Design | 2021-02-19 17:24 | 7 | 0
/Non Project/PSP for Engineers/Program 1 | Code | 2021-02-19 17:31 | 23 | 0
/Non Project/PSP for Engineers/Program 1 | Compile | 2021-02-19 17:54 | 23 | 0

## Defect Recording Log
Proyecto/Tarea | Fecha | ID | Tipo | Inyectado | Eliminado | Tiempo de Arreglo | Cuenta de correcciones | Defecto por Arreglo | Pendiente | DescripciÃ³n
/Non Project/PSP for Engineers/Program 1 | 2021-02-19 | 1 | Documentation | Design | Code | 0.7 | 1 |  |  | The program must recieve any integer greater than 1, NOT any positive integer which includes 0
/Non Project/PSP for Engineers/Program 1 | 2021-02-19 | 2 | Build, package | Code | Compile | 0.2 | 1 |  |  | C:\Python38\python.exe: Error while finding module specification for 'code.fibonacci' (ModuleNotFoundError: __path__ attribute not found on 'code' while trying to find 'code.fibonacci')
/Non Project/PSP for Engineers/Program 1 | 2021-02-19 | 3 | Function | Code | Compile | 6.3 | 1 |  |  | Program recurses infinitely
/Non Project/PSP for Engineers/Program 1 | 2021-02-19 | 4 | Function | Code | Compile | 1.5 | 1 |  |  | Not returning correct value
/Non Project/PSP for Engineers/Program 1 | 2021-02-19 | 5 | Data | Code | Compile | 5.8 | 1 |  |  | Not writing Info on .txt